## GanttChart
Boeing/Clemson VR Training and Simulation | [7 empty] | Gantt Chart Template © 2006-2018 by Vertex42.com.
Boeing South Carolina (BSC) - Charleston Propulsion
Clemson University
| Project Start Date | 2021-01-13 |  |  |  | Display Week | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Lead | Yates | [5 empty] | 2021-01-11 | [6 empty] | 2021-01-18 | [6 empty] | 2021-01-25 | [6 empty] | 2021-02-01 | [6 empty] | 2021-02-08 | [6 empty] | 2021-02-15 | [6 empty] | 2021-02-22 | [6 empty] | 2021-03-01
 | time axis 2021-01-11 to 2021-03-07
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | time axis 2021-01-11 to 2021-03-07
0 | Initial Project Document Received | Everyone |  | 2021-01-13 | 2021-01-13 | 0 | 100%
0 | Initial Meeting with Client | Everyone |  | 2021-02-01 | 2021-02-01 | 0 | 100%
1 | Requirements Gathering and Solution Planning | Yates |  | 2021-02-01 | 2021-02-22 | 22 | 100%
1.1 | Design Project Architecture | Yates |  | 2021-02-08 | 2021-02-21 | 14 | 100%
1.2 | Project Research | Everyone |  | 2021-02-08 | 2021-02-28 | 21 | 100%
2 | VR for Dummies - 1st | Everyone |  | 2021-02-15 | 2021-03-25 | 39 | 100%
2.1 | Iteration Plan | Yates |  | 2021-02-15 | 2021-02-25 | 11 | 100%
2.2 | Sandbox Environment (Developmental Testing) | Everyone |  | 2021-02-22 | 2021-03-11 | 18 | 100%
2.3 | VR Tutorial Walkthrough | Everyone |  | 2021-02-25 | 2021-03-21 | 25 | 100%
2.4 | VR Tutorial Review and Refinement | Everyone |  | 2021-03-19 | 2021-03-25 | 7 | 100%
3 | VR Tooling Stations - 2nd | Everyone |  | 2021-03-22 | 2021-04-12 | 22 | 100%
3.1 | Tooling Station Plan | Yates |  | 2021-03-12 | 2021-03-22 | 11 | 100%
3.2 | Necessary Basic Tooling Stations | Everyone |  | 2021-03-22 | 2021-03-29 | 8 | 100%
3.3 | Low-Level (Refined) Tooling Stations | Everyone |  | 2021-03-26 | 2021-04-04 | 10 | 100%
3.4 | Linear Compilation of Tooling Stations | Everyone |  | 2021-04-05 | 2021-04-10 | 6 | 100%
3.5 | Tooling Station Review and Refinementt | Everyone |  | 2021-04-09 | 2021-04-12 | 4 | 100%
4 | Desktop Application - 3rd | Everyone |  | 2021-04-09 | 2021-04-25 | 17 | 100%
4.1 | Dedicate a Desktop SDK for Desktop App | Everyone |  | 2021-04-09 | 2021-04-15 | 7 | 100%
4.2 | Transfer Scripts to Desktop App | Everyone |  | 2021-04-12 | 2021-04-20 | 9 | 100%
4.3 | Create a Desktop Build for Desktop Users | Everyone |  | 2021-04-21 | 2021-04-23 | 3 | 100%
5 | Documentation | Everyone |  | 2021-04-16 | 2021-04-29 | 14 | 100%
6 | Final Presenatation | Everyone |  | 2021-04-27 | 2021-04-27 | 1 | 100%
6.1 | Final Report and Documentation Handover | Everyone |  | 2021-04-26 | 2021-04-30 | 5 | 100%
Note on A8: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B8: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C8: Task Lead Enter the name of the Task Lead in this column.
Note on D8: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E8: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F8: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G8: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H8: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).